## Sheet1
Related User Story | Task Description | Initial Estimate | Actual Time | Team Member | Amount Remaining After…
[5 empty] | Week 1 | Week 2
I want to be able to add ingredients | Implement functionality for ingredient measurements(Web) | 2 | 3 | Destiny | 0
I want to be able to add ingredients | Implement functionality for ingredient measurements(Desktop) | 1 | 1 | Matthew | 0
I want to be able to view recipes | Create UI for Recipes Page (Web) | 1.5 | 1.5 | Matthew | 0
I want to be able to view recipes | Create UI for Recipes Page (Desktop) | 1 | 1 | Janera | 0
I want to be able to view recipes | Implement functionality to obtain all recipes from database(web & desktop) | 1 | 2 | Destiny
I want to be able to view recipes | Implement functionality to filter and display recipes for owned ingredients(web) | 1 |  | Matthew
I want to be able to view recipes | Implement functionality to filter and display recipes for owned ingredients(desktop) | 1 |  | Janera
| Update erorr validation to use error labels instead of popups (web) | 1 |  | Destiny
| Update desktop UI to change pages instead of using popups | 1 | 0.75 | Janera | 0
| Estimate Totals | 7.5 | 9.25 |  | 0 | 0
[5 empty] | Matthew Total | 3.5
[5 empty] | Destiny Total | 4
[5 empty] | Janera Total | 3