## Sheet1
Related User Story | Task Description | Initial Estimate | Actual Time | Team Member | Amount Remaining After…
[5 empty] | Week 1 | Week 2
I want to be able to login | Create login page UI for web application | 1 | 1.5 | Destiny | 0 | 0
I want to be able to login | Create login page UI for desktop application | 1 | 0.5 | Matthew | 0.5 | 0
I want to be able to login | Complete validation functionality for login credentials (web & desktop) | 1.5 | 1.5 | Destiny | 1 | 0
I want to be able to login | Complete password hashing functionality | 2 | 1.5 | Matthew | 1.5 | 0
I want to be able to logout | Complete logout funtionality (desktop and web) | 0.5 | 1 | Destiny | 0 | 0
I want to be able to view ingredients | Create ingredients page UI for web application | 2 | 1.5 | Matthew | 1.5 | 0
I want to be able to view ingredients | Complete functionality to show all ingredients a user currently has (web) | 1.5 | 1 | Matthew | 1 | 0
I want to be able to view ingredients | Create ingredients page UI for desktop application | 1 | 1 | Destiny | 1 | 0
I want to be able to view ingredients | Complete functionality to show all ingredients a user currently has (desktop) | 1 | 1 | Destiny | 1 | 0
I want to be able to add ingredients | Create a popup for desktop application | 1 | 1 | Janera | 1 | 0
I want to be able to add ingredients | Complete functionality to add ingredient to list of available ingredients (web) | 1.5 | 5 | Matthew | 5 | 0
I want to be able to add ingredients | Create a popup for web application | 1 | 1 | Janera | 1 | 0
I want to be able to add ingredients | Complete functionality to add ingredient to list of available ingredients (desktop) | 1 | 1 | Janera | 1 | 0
I want to be able to remove ingredients | Complete functionality for removing ingredients | 1 | 1 | Janera | 1 | 0
I want to be able to update quantity/amount of ingredients | Complete functionality to update quantity/amount (desktop) | 1 | 1 | Janera | 1 | 0
I want to be able to update quantity/amount of ingredients | Complete functionality to update quantity/amount (web) | 1 | 1 | Janera | 1 | 0
I want to be able to register a user | Create UI for to register new user on web application | 1.5 | 1.5 | Destiny | 1.5 | 0
I want to be able to register a user | Create functionality to register new user on web application | 2 | 2 | Destiny | 1.5 | 0
I want to be able to register a user | Create UI for to register new user on desktop application | 0.1 | 0.1 | Matthew | 0.1 | 0
I want to be able to register a user | Create functionality to register new user on desktop application | 0.5 | 0.5 | Matthew | 0.5 | 0
| Estimate Totals | 22.1 |  |  | 22.1 | 0
[5 empty] | Matthew Total | 8.6
[5 empty] | Destiny Total | 7.5
[5 empty] | Janera Total | 6