## Sheet1
Related User Story | Task Description | Initial Estimate | Assigned Team Member | Actual Time | Completed By | Notes | Amount Remaining After…
[7 empty] | Week 1 | Week 2
I want to be able to view planned meals | Create UI for planned meals page(Desktop) | 1.5 | Janera | 1.5 | Janera |  | 1.5 | 0
I want to be able to view planned meals | Create UI for planned meals page(web) | 2 | Matthew | 1 | Matthew |  | 0 | 0
I want to be able to view planned meals | Implement functionality for view planned meals(Dekstop) | 3 | Janera | 3 | Janera |  | 3 | 0
I want to be able to view planned meals | Implement functionality for view planned meals(Web) | 2.5 | Matthew | 6 | Matthew |  | 2.5 | 0
I want to be able to filter recipes | Implement functionality to filter recipes by tags(Web) | 3 | Destiny | 5 | Destiny |  | 3 | 0
I want to be able to filter recipes | Implement functionality to filter recipes by tags(Desktop) | 1.5 | Janera | 1.5 | Destiny |  | 1.5 | 0
I want to be able to filter recipes | Modify Recipe page desktop UI to use checkbox and button instead of radio buttons | 1 | Janera | 1 | Matthew |  | 1 | 0
I want to be able to filter recipes | Modify Recipe page Web UI to use checkbox and button instead of radio buttons | 1 | Destiny | 1 | Destiny |  | 1 | 0
I want to be able to filter recipes | Modify functionality to fit new Desktop UI for filtering recipes on Recipe page | 1 | Matthew | 1 | Matthew |  | 1 | 0
I want to be able to filter recipes | Modify functionality to fit new Web UI for filtering recipes on Recipe page | 4 | Destiny | 4 | Destiny |  | 4 | 0
I want to be able to add to planned meals | Implement functionality to add recipe to a specific day of the week for planned meals(desktop) | 1.5 | Janera | 8 | Janera |  | 2.5 | 0
I want to be able to add to planned meals | Implement functionality to add recipe to a specific day of the week for planned meals(web) | 1.5 | Matthew | 1.5 | Matthew |  | 1.5 | 0
I want to be able to view different pages of recipes | Implement functionality to make recipe list paginated(Desktop) | 1.5 | Janera | 1 | Matthew |  | 1.5 | 0
I want to be able to view different pages of recipes | Implement functionality to make recipe list paginated(Web) | 2 | Matthew | 6 | Matthew |  | 0 | 0
Feedback | Modify database tables to use a pivot table containg shared data for an ingredient | 0.5 | Destiny | 0.5 | Destiny |  | 0.5 | 0
Feedback | Modify model classes and SQL functionality to work with new table structures | 1.5 | Destiny |  | Destiny |  | 1.5
Feedback | Fix Use Cases | 0.5 | Matthew | 0.5 | Matthew |  | 0.5 | 0
Feedback | Update tests to raise test coverage | 1 | Matthew | 1 | Matthew |  | 1 | 0
Feedback | Add approriatate and informative documentaion to classes and methods | 1.5 | Matthew | 1.5 | Matthew |  | 1.5
Feedback | Fix issues with accessing projects in Test Project | 2 | Destiny | 2 | Destiny | Waiting for assistance from Corley to figure out issue with accessing Web and Desktop projects in the Test Project. | 2 | 1
Feedback | Update class diagram to include a more detailed representaion of project file | 2 | Janera |  | Janera
| Estimate Totals | 32.5 |  | 47 |  |  | 31 | 1
| Team Member | Estimated Total | Completed Total
| Matthew | 12 | 14.5
| Destiny | 12 | 13.5
| Janera | 12 | 8