## Sheet1
Related User Story | Task Description | Initial Estimate | Assigned Team Member | Actual Time | Completed By | Notes | Amount Remaining After…
[7 empty] | Week 1 | Week 2
Add to shopping list / remove from shopping list | Complete functionaliy to add and remove an ingredient from the shopping list | 1 | Matthew
Add to shopping list / remove from shopping list | Complete functionaliy to add and remove an ingredient from the shopping list (desktop) | 1 | Destiny
Add planned meal ingredients to shopping list | Create functionality to add needed ingredients from planned meals to shpping list (web) | 1.5 | Matthew
Add planned meal ingredients to shopping list | Create functionality to add needed ingredients from planned meals to shpping list (desktop) | 1.5 | Janera
View shopping list | Create UI to view current shopping list for web application | 0.5 | Destiny | 1 | Destiny |  | 0 | 0
View shopping list | Create UI to view current shopping list for desktop application | 0.5 | Destiny
View shopping list | Complete functionalty to view current shopping list for web application | 1 | Destiny | 1 | Destiny |  | 0 | 0
View shopping list | Complete functionalty to view current shopping list for desktop application | 0.5 | Destiny
Add all shopping list ingredients to pantry | Compete functionality to add all shopping list ingredients to pantry (web) | 0.5 | Matthew
Add all shopping list ingredients to pantry | Compete functionality to add all shopping list ingredients to pantry (desktop) | 0.5 | Janera
Remove ingredients used to cook recipe | Complete functionality to remove ingredients used to cook recipe from pantry (web) | 0.5 | Destiny
Remove ingredients used to cook recipe | Complete functionality to remove ingredients used to cook recipe from pantry (desktop) | 0.5 | Janera
Add new recipe | Complete functionality add an new recipe (web) | 1 | Matthew
Add new recipe | Complete functionality add an new recipe (desktop) | 0.5 | Matthew
Share a recipe | Complete functionality to share a recipe (desktop)
Share a recipe | Complete functionality to share a recipe (web) | 0.5 | Destiny
Share a recipe | Create UI to view shared recipes (desktop)
Share a recipe | Create UI to view shared recipes (web) | 1 | Destiny
Documentation | Complete Use cases and use case diagram | 1 | Matthew | 1 | Matthew |  | 0 | 0
Documentation | Complete Class Diagram | 2 | Janera
Documentation | Complete erd | 1 | Destiny | 1 | Destiny |  | 0 | 0
Demo Feedback | Fix issues with desktop application mentioned in demo | 1 | Janera
Feedback
Feedback
| Estimate Totals | 17.5 |  | 4 |  |  | 0 | 0
| Team Member | Estimated Total | Completed Total
| Matthew | 5.5 | 1
| Destiny | 6 | 2.5
| Janera | 5.5 | 0