## Sheet1
Related User Story | Task Description | Initial Estimate | Actual Time | Team Member | Amount Remaining After…
[5 empty] | Week 1 | Week 2
I want to be able to view planned meals | Create UI for planned meals page(Desktop) | 1 | 1.5 | Janera | 1 | 0
I want to be able to view planned meals | Create UI for planned meals page(web) | 2 | 1 | Matthew | 0 | 0
I want to be able to view planned meals | Implement functionality for view planned meals(Dekstop) | 3 | 9 | Janera | 2.5 | 0
I want to be able to view planned meals | Implement functionality for view planned meals(Web) | 3 | 6 | Matthew | 2.5 | 0
I want to be able to filter recipes | Implement functionality to filter recipes by tags(Web) | 2 | 5 | Destiny | 1 | 0
I want to be able to filter recipes | Implement functionality to filter recipes by tags(Desktop) | 1.5 | 1.5 | Destiny | 1.5 | 0
I want to be able to filter recipes | Modify Recipe page desktop UI to use checkbox and button instead of radio buttons | 0.5 | 0.5 | Matthew | 0.5 | 0
I want to be able to filter recipes | Modify Recipe page Web UI to use checkbox and button instead of radio buttons | 1 | 1 | Destiny | 1 | 0
I want to be able to filter recipes | Modify functionality to fit new Desktop UI for filtering recipes on Recipe page | 0.5 | 0.5 | Matthew | 1 | 0
I want to be able to filter recipes | Modify functionality to fit new Web UI for filtering recipes on Recipe page | 3 | 4 | Destiny | 3 | 0
I want to be able to add to planned meals | Implement functionality to add recipe to a specific day of the week for planned meals(desktop) | 1.5 | 8 | Janera | 1.5 | 0
I want to be able to add to planned meals | Implement functionality to add recipe to a specific day of the week for planned meals(web) | 1.5 | 1.5 | Matthew | 2 | 0
I want to be able to view different pages of recipes | Implement functionality to make recipe list paginated(Desktop) | 1.5 | 1 | Matthew | 1 | 0
I want to be able to view different pages of recipes | Implement functionality to make recipe list paginated(Web) | 2 | 6 | Matthew | 0 | 0
| Fix testing problems | 3 |  | Destiny | 3 | 3
| Estimate Totals | 24 | 46.5 |  | 21.5 | 3
[5 empty] | Matthew Total | 11
[5 empty] | Destiny Total | 10.5
[5 empty] | Janera Total | 5.5