## Sheet1
Related User Story | Task Description | Initial Estimate | Actual Time | Team Member | Amount Remaining After…
[5 empty] | Week 1 | Week 2
I want to be able to view planned meals | Create UI for planned meals page(Desktop) | 1 |  | Janera
I want to be able to view planned meals | Create UI for planned meals page(web) | 2 |  | Matthew
I want to be able to view planned meals | Implement functionality for view planned meals(Dekstop) | 2.5 |  | Janera
I want to be able to view planned meals | Implement functionality for view planned meals(Web) | 3 |  | Matthew
I want to be able to filter recipes | Implement functionality to filter recipes by tags(Web) | 2 |  | Destiny
I want to be able to filter recipes | Implement functionality to filter recipes by tags(Desktop) | 1.5 |  | Janera
I want to be able to add to planned meals | Implement functionality to add recipe to a specific day of the week for planned meals(desktop) | 1.5 |  | Janera
I want to be able to add to planned meals | Implement functionality to add recipe to a specific day of the week for planned meals(web) | 2 |  | Destiny
I want to be able to view different pages of recipes | Implement functionality to make recipe list paginated(Desktop) | 1 |  | Janera
I want to be able to view different pages of recipes | Implement functionality to make recipe list paginated(Web) | 2 |  | Matthew
| Fix testing problems | 3 |  | Destiny
| Estimate Totals | 18.5 | 0 |  | 0 | 0
[5 empty] | Matthew Total | 7
[5 empty] | Destiny Total | 7
[5 empty] | Janera Total | 7.5